## READ ME FIRST
READ ME FIRST
Purpose
This workbook provides a structured way for the Project Manager and Executive Sponsor to assess current project leadership practices and identify practical development priorities that reduce project friction and improve delivery outcomes.
Who this is for
This workbook is intended to be completed by:
* Project Manager (PM Self-Assessment)
* Executive Sponsor (Executive Assessment)
Psychological safety (important)
This is not a performance review and is not meant to “grade” anyone. The goal is to surface alignment gaps and focus areas so the PM and sponsor can agree on where to improve support, clarity, and execution.
What’s inside
1. PM Self-Assessment Instructions
2. PM Self-Assessment
3. Executive Assessment Instructions
4. Executive Assessment
Recommended completion sequence
Step 1: PM completes the PM_Self_Assessment first. Step 2: Sponsor completes the Executive_Assessment after the PM finishes. This sequencing helps keep the process independent and reduces bias.
How to use the results (two options)
Option A: DIY (internal use): Use the completed assessments to identify the top 5–10 priority areas and agree specific next steps.
Option B: Optional FREE PDF summary: If you would like a consolidated PDF summary of both perspectives, email the completed workbook and I will generate and return the summary at no cost.
Time required
PM Self-Assessment: 20–30 minutes
Executive Assessment: 20–30 minutes
Privacy
If you email the workbook for a summary, it will be used only to produce your PDF summary and will not be shared.

## PM Instructions
PM SELF-ASSESSMENT
Instructions
OVERVIEW:
Your executive/manager has requested this self-assessment as part of your development planning.
This is NOT a performance review - there are no "wrong" answers.
We want your honest self-evaluation to identify where coaching support would be most valuable.
HOW TO COMPLETE: (Enter information only in )
1. Go to "PM_Self_Assessment" tab
2. Review each of the 40 project management competence statements
3. Rate yourself on each using the 1-5 scale (dropdown menu provided)
4. Be honest - this helps identify development priorities
5. Should take 20-30 minutes
6. Return completed file to your manager by the requested date
SCORING GUIDE:
1 = Never - I don't do this / don't know how to do this
2 = Rarely - I know I should but struggle to do it consistently
3 = Inconsistently - I can do this but it's not yet a reliable habit
4 = Consistently - I do this reliably on most projects
5 = Always - This is a strength; I do this naturally and effectively
BE HONEST:
Scores of 2-3 are normal and expected - these represent development opportunities.
This assessment helps identify where coaching would provide the most value.
CONFIDENTIALITY:
Your responses will be compared with your executive/manager's assessment to identify development
priorities. Results are used only for development planning purposes.
QUESTIONS?
Contact your executive/manager if you have questions about any competence statement.
ESTIMATED TIME: 20-30 minutes
Thank you for taking the time to complete this assessment thoughtfully!
Yellow-colored cells

## PM_Self_Assessment
PM Self-Assessment (1–5)
Name:
Date:
Gap # | Functional Area | BRIDGE Module | PM-Perspective Competence Statement | PM Score (1-5) | Evidence / Example (Optional)
1 | Benefits Realization | B | I focus on delivering business outcomes and value, not just completing deliverables
2 | Benefits Realization | B | I translate technical work into business language that stakeholders understand
3 | Business & Organizational Context | B | I take time to learn and understand the business processes and workflows
4 | Business & Organizational Context | B | I speak the business language, not just PM or technical jargon
5 | Project Reporting & Analytics | B | I track meaningful KPIs that matter to the business, not vanity metrics
6 | Project Reporting & Analytics | B | I track and report leading indicators to enable proactive decision-making
7 | Project Communication | B | I use visuals effectively to communicate complex information clearly
8 | Risk | R | I proactively identify and address risks before they become issues
9 | Risk | R | I clearly distinguish between risks, issues, and assumptions in my planning
10 | Risk | R | I develop detailed response plans for identified risks, not just list them
11 | Resources | R | I advocate for and secure the resources my project actually needs
12 | Resources | R | I effectively retain key resources and resist mid-project resource changes
13 | Issue Management | R | I clearly distinguish current issues from potential future risks
14 | Issue Management | R | I track clear ownership and accountability for every issue requiring resolution
15 | Issue Management | R | I focus on root causes of problems, not just symptoms
16 | Issue Management | R | I engage issue owners to drive resolution rather than solving everything myself
17 | Quality | R | I build quality into the process from the start, not just inspect at the end
18 | Quality | R | I engage actual end users in quality validation and testing activities
19 | Quality | R | I establish and enforce quality gates between project phases
20 | Stakeholder Management | I | I clearly distinguish decision-makers from influencers in my stakeholder engagement
21 | Stakeholder Management | I | I brief stakeholders privately before raising issues in status meetings
22 | Project Communication | I | I communicate bad news clearly and directly, not buried in excessive detail
23 | Change Management | I | I plan for the messy transition period and manage organizational change effectively
24 | Procurement | I | I understand and plan for procurement lead times well in advance
25 | Procurement | I | I actively manage vendor relationships beyond just contractual requirements
26 | Team Leadership | G | I manage and develop people as individuals, not just tasks and activities
27 | Performance Management | G | I provide regular, timely performance feedback to my team members
28 | Governance | D | I follow governance processes and obtain proper approvals even when they slow me down
29 | Scope | D | I effectively manage scope and push back on requests when necessary
30 | Scope | D | I enforce formal change processes even for "small" changes
31 | Schedule | D | I proactively identify and manage schedule risks before dates start slipping
32 | Schedule | D | I provide nuanced schedule status reporting beyond simple green/yellow/red
33 | Change Control | D | I ensure all changes are formally documented before implementation
34 | Change Control | D | I communicate approved changes broadly to all affected stakeholders
35 | Vendor/Contract Management | E | I proactively manage vendor dependencies on project team deliverables
36 | Vendor/Contract Management | E | I plan for and ensure effective knowledge transfer from vendors to internal teams
37 | Vendor/Contract Management | E | I closely track vendor costs against contract budgets to avoid surprises
38 | Data Management | E | I establish clear data governance frameworks for the project
39 | Data Management | E | I ensure data quality and accuracy throughout the project lifecycle
40 | Logistics | E | I plan for physical and logistical dependencies well in advance

## Executive Instructions
PM CAPABILITY ASSESSMENT
Executive Instructions
OVERVIEW: You are assessing your Project Manager across 40 critical competence gaps organized by the BRIDGE Framework (Bridge Gaps, Reframe Chaos, Influence Stakeholders, Drive Decisions, Grow Trust, Execute Strategically).
This assessment helps you decide the most appropriate support approach: training, coaching, or role-change consideration, based on evidence.
HOW TO COMPLETE: (Enter information only in Yellow-colored cells )
Step 1: PM completes Self-Assessment first (recommended)
1. Send this workbook to your PM and ask them to complete the PM_Self_Assessment tab first.
2. Ask the PM to return the workbook to you after they have completed their section.
Step 2: Executive completes this assessment 3. After receiving the PM-completed workbook, go to the “Executive_Assessment” tab. 4. Review each of the 40 competence gaps. 5. Rate your PM using the 1–5 scale (dropdown menu provided). 6. (Optional) Add brief examples in the Evidence column (bullets are fine). 7. Complete the assessment in one sitting if possible for consistency.
Step 3: Use internally, or request an optional readout 8. When both assessments are complete, you may either:
* Use it internally to guide a sponsor–PM discussion, or
* Email the completed workbook to request an optional consolidated PDF readout.
SCORING GUIDE: 1 = Never – PM doesn’t know this practice exists (knowledge gap) 2 = Rarely – PM knows it but struggles with execution ★ often a coaching candidate 3 = Inconsistently – PM can do it but it’s not yet a reliable habit ★ often a coaching candidate 4 = Consistently – PM does this well; minor refinement only 5 = Always – PM has mastered this; not a development area
KEY INSIGHT: Scores of 2-3 are often ideal for coaching because the PM generally understands the practice but needs support building consistency under real project pressure. Scores of 1 may indicate the need for foundational training before coaching will be effective.
IMPORTANT (Free Version): This workbook includes the PM Self-Assessment and Executive Assessment. A consolidated dashboard/readout can be created after both perspectives are completed (either for internal use, or as an optional PDF summary).
NEXT STEPS (Recommended): After both assessments are completed, review and align on:
* Overall readiness for coaching
* Top 10 priority development areas
* Recommended support approach (train / coach / role-fit)
* Expected timeline and outcomes
QUESTIONS / OPTIONAL READOUT: Email the completed workbook and I’ll send you a consolidated PDF summary - FREE. A live debrief session is optional and can be scheduled separately.
Dr. Pernel Roberts | pernel@moreprojectsuccess.com
Yellow-colored cells

## Executive_Assessment
Executive Assessment (1–5)
Executive:
PM Name:
Date:
Gap # | PM Competence Gap | Score (1-5) | Priority (Auto) | Evidence / Example (Optional) | Priority logic (auto)
1 | PM focuses only on deliverables, not business outcomes - 'done' means delivered, not value achieved |  |  |  | Label | Meaning
2 | PM can't translate technical deliverables into business language - speaks IT/project jargon only |  |  |  | 🔴 NOT READY | Score = 1 (knowledge gap)
3 | PM doesn't learn business processes and workflows - manages in complete vacuum |  |  |  | 🟢 HIGH PRIORITY | Score = 2–3 (ideal coaching target)
4 | PM doesn't speak the business language - uses only PM/technical jargon |  |  |  | 🟡 MEDIUM PRIORITY | Score = 4 (refinement)
5 | PM tracks vanity metrics not meaningful KPIs - measures what's easy not what matters |  |  |  | ⚪ LOW PRIORITY | Score = 5 (maintain excellence)
6 | PM doesn't track leading indicators - only reports lagging results when it's too late
7 | PM doesn't use visuals effectively - walls of text that nobody reads or understands
8 | PM operates in 'hope mode' - doesn't proactively identify risks before they materialize
9 | PM doesn't distinguish between risks, issues, and assumptions - treats everything the same
10 | PM doesn't develop risk response plans - just identifies risks and hopes they don't happen
11 | PM accepts whatever resources offered - doesn't fight for what's actually needed
12 | PM can't retain key resources - functional managers pull people mid-project without effective resistance or escalation
13 | PM doesn't distinguish issues from risks clearly - treats current problems as future risks
14 | PM doesn't track issue resolution ownership clearly - issues sit in limbo with no clear owner
15 | PM focuses on symptoms not root causes - same issues recur repeatedly
16 | PM doesn't engage issue owners to drive resolution - PM tries to solve everything personally
17 | PM treats quality as last-minute inspection activity - defects only found late in delivery cycle
18 | PM doesn't engage actual end users in quality validation - relies solely on technical testing
19 | PM doesn't establish quality gates between phases - defective work proceeds despite quality failures
20 | PM doesn't distinguish decision-makers from influencers - wastes time consulting wrong people
21 | PM ambushes stakeholders in status meetings with issues against their names - no prior private briefing
22 | PM buries bad news in excessive detail - hoping nobody notices problems hidden in data dump
23 | PM doesn't plan for messy transition period - flips switch overnight and expects immediate new steady state
24 | PM doesn't understand procurement lead times - suddenly needs vendor 'yesterday' with no planning
25 | PM doesn't actively manage vendor relationship - treats as arms-length contractual transaction only
26 | PM manages tasks and activities not people - treats team members as interchangeable resource units
27 | PM doesn't provide regular performance feedback - only during crisis or annual review
28 | PM bypasses governance processes for 'speed' - makes commitments without approval
29 | PM says 'yes' to every request - scope creep completely unchecked and unmanaged
30 | PM allows 'small' changes without formal process - death by thousand cuts
31 | PM doesn't proactively manage schedule risks - only reacts when dates already slipping
32 | PM reports schedule status as simple green/yellow/red with no nuance - binary assessment only
33 | PM lets changes happen informally without documentation - 'just do it now, we'll document later sometime'
34 | PM doesn't communicate approved changes broadly to affected parties - team doesn't know what changed
35 | PM doesn't manage vendor dependencies on project team - vendors blocked waiting for project inputs
36 | PM doesn't prepare for vendor knowledge transfer - knowledge stays trapped with vendor
37 | PM doesn't track vendor costs against contract budget - vendor cost surprises at billing
38 | PM doesn't establish data governance - everyone manages their own data their own way
39 | PM doesn't ensure data quality and accuracy - garbage in, garbage out
40 | PM doesn't plan physical and logistical dependencies - assumes facilities, equipment, space will magically appear
B
R
I
D
G
E